## Sheet1
Project Name: Digital Earth South Africa
Project Objective:
Project Number: CP202405
Project Leader: Indiphile Ngqambuza
Activity | Task | Human Resource | Task Start Date | Sprint/Days | Task End Date | Activity Completion Date | CAPEX | Comments
Open Data Cube Research | Low & high-level ODC architecture | Indiphile Ngqambuza & Moloko Sebake | 2024-06-10 | 5 days | 2024-06-14 | 2024-06-14 |  | Core ODC project and Existing Deployments
| ODC Applications & Data Flow | Indiphile Ngqambuza & Moloko Sebake | 2024-06-10 | 5 days | 2024-06-14 | 2024-06-14
DESA Infrastuture Assement | DESA Infrastructure and Applications | Indiphile Ngqambuza & Karabo Mithi | 2024-06-17 | 5 days | 2024-06-21 | 2024-06-21 |  | Current Deployment and Issues.
| Current Environment Configuration | Indiphile Ngqambuza & Karabo Mithi |  |  |  | 2024-06-21
DESA System Design | ODC Components & DESA Integrated System Design | Indiphile Ngqambuza, Maite Marageni and Asanda Lamba, | 2024-06-24 | 5 days | 2024-06-28 | 2024-06-28 |  | Frontend,backend, APIs and Databas Schemas
| DESA ARD Dataflow | Karabo Mithi , Indiphile Ngqambuza | 2024-06-24 | 5 days | 2024-06-28 | 2024-06-28 |  | Dataset Format, Data Ingesting, Flow and Publication
DESA System Development | Setup Developmnt Environment | Indiphile Ngqambuza, Tebogo Ramokgopa & Karabo Mithi | 2024-07-01 | 5 days | 2024-07-05 | 2024-09-06 |  | Available SANSA Infrastructure. Resource provision
| DESA Backend Software Components | Indiphile Ngqambuza & Asanda Lamba | 2024-07-08 | 10 days | 2024-07-19 | 2024-09-06 |  | Custom ODC Applications, Databases
| DESA System Integration | Indiphile Ngqambuza & Asanda Lamba | 2024-07-22 | 10 days | 2024-08-02 | 2024-09-06 |  | Integrated DESA System - Docker Compose
| DESA User Interface Design | Indiphile Ngqambuza & Maite Marageni | 2024-08-12 | 5 days | 2024-08-16 | 2024-09-06 |  | Prototype & Procurement of UI Development Tools
| Frontend Development | Indiphile Ngqambuza & Maite Marageni | 2024-08-19 | 10 days | 2024-08-30 | 2024-09-06 |  | Frontend and Backend Integration
| Build & Run Develoment Release | Indiphile Ngqambuza | 2024-09-02 | 5 days | 2024-09-06 | 2024-09-06 |  | Docker Compose, Demonstration
DESA System Testing | Test Planning & Strategy | Indiphile Ngqambuza | 2024-09-09 | 5 days | 2024-09-13 | 2024-10-11 |  | Types of Test, Tools to be used
| Test Case Development | Moloko Sebake & Indiphile Ngqambuza | 2024-09-16 | 5 days | 2024-09-20 | 2024-10-11 |  | Test and Review outcomes
| Unit Test | Indiphile,Asanda Lamba,Maite Marageni | 2024-09-23 | 5 days | 2024-09-27 | 2024-10-11 |  | Frontend and Backend components
| Integration Test | Indiphile,Asanda Lamba,Maite Marageni | 2024-09-30 | 5 days | 2024-10-04 | 2024-10-11 |  | Verify the Interactions between Different Components
| Functional Testing | Indiphile,Asanda Lamba,Maite Marageni | 2024-10-07 | 5 days | 2024-10-11 | 2024-10-11 |  | Validate Functionality
DESA System Deployment | Setup Prod Environments | Indiphile Ngqambuza ,Karabo Mithi & Tebogo Ramokgopa | 2024-10-14 | 5 days | 2024-10-18 | 2024-11-29 |  | Create Physical Or Virtual VMs
| Deployment Planning | Indiphile Ngqambuza | 2024-10-21 | 5 days | 2024-10-25 | 2024-11-29 |  | K8s Cluster Design, Deployment Strategies( Rolling, Blue-Green)
| Setup Environment | Indiphile Ngqambuza ,Karabo Mithi & Tebogo Ramokgopa | 2024-10-28 | 5 days | 2024-11-01 | 2024-11-29 |  | Setup Staging and Production Environment
| Deploy to Staging Enviroment | Indiphile Ngqambuza | 2024-11-04 | 5 days | 2024-11-08 | 2024-11-29 |  | Deploy the Latest the Build
| User Acceptance Testing(UAT) | EO stuff | 2024-11-11 | 5 days | 2024-11-15 | 2024-11-29 |  | Validate Functionality
| Deploy to Production Enviroment | Indiphile Ngqambuza | 2024-11-18 | 5 days | 2024-11-22 | 2024-11-29 |  | External Access, Secret Management(API keys,Password)
| Configure Monitoring Tools | Indiphile , Karabo Mithi, Tebogo Ramokgopa | 2024-11-25 | 5 days | 2024-11-29 | 2024-11-29 |  | E.g Grafana
DESA Documentation | Existing DESA Documentation | Maite Marageni & Indiphile Ngqambuza | 2024-12-02 | 5 days | 2024-12-06 | 2025-01-31
| Edit And Publish the Documentaion | Maite Marageni & Indiphile Ngqambuza | 2025-12-09 | 10 days | 2025-12-20 | 2025-01-31 |  | Creating user guides and tutorials( e.g videos)
| Project Review & Closure | Moloko Sebake | 2025-01-13 | 5 days | 2025-01-17 | 2025-01-31 |  | Approvals and project closure